## Timeline
Tasks | Actions | [6 empty] | Beneficiary
| GT0. Project Preparatory | WP1: Development of a thematic networking in SUDOE | WP2: Development of tools to support the transition to a LCE in schools | WP3: Implementation of a methodology conducting to a LCE in 35 pilot schools | WP.T1. Project Management | WP.T2. Project Communication | WP.T3. Project Monitoring and Evaluation | 1. IST | 2. ISQ | 3. EDIGREEN | 4. ABAE | 5. CIEMAT | 6. USE | 7. ULR | 8. VLR | 9. UG | 2015 |  |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[17 empty] | m-9 | m-8 | m-7 | m-6 | m-5 | m-4 | m-3 | m-2 | m-1 | m0 | m1 | m2 | m3 | m4 | m5 | m6 | m7 | m8 | m9 | m10 | m11 | m12 | m13 | m14 | m15 | m16 | m17 | m18 | m19 | m20 | m21 | m22 | m23 | m24 | m25 | m26 | m27 | m28 | m29 | m30 | m31 | m32 | m33 | m34 | m35 | m36
[17 empty] | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | june
WP0 Preparation | ● | [6 empty] | 1 | ● | ● | ● | ● | ● | ● | ● | ● | bar: 2015 m-9 to 2016 m-5
WP 1.1 Development of a Web Portal |  | ● | [5 empty] | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2016 m4: P1.1/E1.1.1
WP 1.2 Focus Group Discussion |  | ● | [5 empty] | ● | ● | ● | ● | ● | ● | ● | ● | 1 | 2019 m35: E1.2.1
WP 1.3 Network with other projects |  | ● | [5 empty] | ● | ● | ● | ● | ● | ● | ● | ● | 1 | 2016 m3: E1.3.1; 2016 m4: P1.2; 2019 m35: E1.3.2
WP 1.4 ClimACT Academy |  | ● | [5 empty] | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2017 m7: P1.4; 2017 m10: P1.7; 2017 m12: P1.5/1.8; 2017 m15: P1.6; 2017 m16: P1.9; 2018 m24: P1.10; 2019 m34: E1.4.1
WP 1.5 ClimACT Resource-matching platform |  | ● | [5 empty] | ● | 1 | ● |  |  | ● |  | ● |  | 2017 m12: P1.11/E1.5.1
WP 2.1 Development of the ClimACT decision support tool |  |  | ● |  |  |  |  | ● | ● | 1 | ● | ● | ● | ● |  | ● | 2016 m3: E2.1.1; 2017 m11: E2.1.2/2.1.3; 2019 m34: P2.1
WP 2.2 Database Module |  |  | ● |  |  |  |  | ● | ● | 1 | ● | ● | ● | ● |  | ● | 2016 m6: E2.2.1; 2019 m34: E2.2.2
WP 2.3 KPI Generator Module |  |  | ● |  |  |  |  | ● | ● | 1 |  | ● | ● | ● |  | ● | 2016 m5: E2.3.1; 2017 m8: D2.3.2; 2017 m13: P2.2
WP 2.4 Building Scenario Module |  |  | ● |  |  |  |  | ● | ● | 1 |  | ● | ● | ● |  | ● | 2017 m9: E2.4.1
WP 2.5 Life Cycle Assessment Module |  |  | ● |  |  |  |  | ● | ● | ● |  | 1 |  |  |  |  | 2017 m9: E2.5.1
WP 2.6 Cost Benefit Assessment Module |  |  | ● | [5 empty] | ● | ● |  | 1 |  |  |  |  | 2017 m10: E2.6.1; 2017 m18: P2.3
WP 2.7 Development of new business models and management strategies |  |  | ● | [5 empty] | 1 | ● |  |  | ● |  |  |  | 2017 m12: P2.4/D2.7.1/.2
WP 2.8 Development of the ClimACT educational platfotm for active learning |  |  | ● |  |  |  |  | ● | ● | ● | 1 | ● |  |  | ● | ● | 2016 m4: E2.8.1; 2017 m12: P2.5; 2017 m13: P2.6
WP 2.9 E-learning module for teachers on sustainable development |  |  | ● |  |  |  |  | ● | ● | ● | 1 | ● |  |  | ● | ● | 2017 m9: E2.9.1
WP 2.10 Classroom training module |  |  | ● |  |  |  |  | ● | ● | ● | 1 | ● |  |  | ● | ● | 2017 m11: E2.10.1/2.10.2
WP 2.11 Gamification module |  |  | ● |  |  |  |  | ● | ● | ● | 1 | ● |  |  | ● | ● | 2017 m11: E2.11.1/2.11.2
WP 3.1 Commitment to a policy conducting to a LCE in schools |  |  |  | ● |  |  |  | ● |  |  | 1 | ● | ● |  | ● | ● | 2016 m6: E3.1.1
WP 3.2 Assessment baseline in energy, environment and CO2 emissions performance, audits and benchmarking |  |  |  | ● |  |  |  | 1 | ● | ● | ● | ● | ● | ● |  | ● | 2017 m7: E3.2.1; 2017 m12: E3.2.2
WP 3.3 Definition of targets and development of action plans |  |  |  | ● |  |  |  | ● | ● | ● | ● | ● | 1 | ● | ● | ● | 2017 m18: E3.3.1/3.3.2
WP 3.4 Implementation of action plans |  |  |  | ● |  |  |  | ● | ● | ● | ● | ● | 1 | ● | ● | ● | 2018 m26: E3.4.1
WP 3.5 Progress evaluation |  |  |  | ● |  |  |  | ● | ● | ● | ● | ● | 1 | ● | ● | ● | 2019 m33: P3.1/E3.5.1; 2019 m34: P3.2/3.3/3.4
T 1.1 Structure, responsabilities and procedures for the management and daily coordination of the project |  |  |  |  | ● |  |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | bar: 2016 m1 to 2019 m36
T 1.2 Bodies created for political and technical decision and their skills |  |  |  |  | ● |  |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | bar: 2016 m1 to 2019 m36
T 1.3 Internal communication |  |  |  |  | ● |  |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | bar: 2016 m1 to 2019 m36
T 1.4 Financial magagement |  |  |  |  | ● |  |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | bar: 2016 m1 to 2019 m36
T 2.1 Logo creation | [5 empty] | ● |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2016 m3: ET2.1.1
T 2.2 Website | [5 empty] | ● |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2016 m3: ET2.2.1
T 2.3 Dissemination Event | [5 empty] | ● |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2019 m35: ET2.3.1
T 2.4 Poster A3 | [5 empty] | ● |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2016 m2: ET2.4.1
T 2.5 Dissemination Activities | [5 empty] | ● |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2019 m36: ET2.5.1
T 2.6 Dissemination and Communication Plan | [5 empty] | ● |  | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2019 m36: ET2.6.1
T 3.1 Structure, responsabilities and procedures to monitor the project | [6 empty] | ● | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2016 m2: ET3.1.1
T 3.2 Structure, responsabilities and procedures to evaluate the project | [6 empty] | ● | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2019 m36: ET3.2.1
T 3.3 Procedures for risk management and quality control | [6 empty] | ● | 1 | ● | ● | ● | ● | ● | ● | ● | ● | 2016 m2: ET3.3.1

## Products
Products
| Ref | Name | Deadline |  |  | Responsible
WP1 | P1.1 | ClimACT Gateway | 2016 | October | M4 | IST
| P1.2 | Network of stakeholders,end-users and other project teams | 2016 | October | M4 | UniGib
| P1.4 | ClimACT Academy Infrastructue | 2017 | January | M7 | IST
| P1.5 | Training course on the ClimACT decision support tool operation | 2017 | June | M12 | Edigreen
| P1.6 | Seminar on business models for ESCO | 2017 | September | M15 | ISQ
| P1.7 | E-learning course on Sustainable Development | 2017 | April | M10 | ABAE
| P1.8 | Training course on the ClimACT educational tools operation | 2017 | June | M12 | ABAE
| P1.9 | Awareness campaigns with presentation of ClimACT gamification approaches | 2017 | October | M16 | ABAE
| P1.10 | Awareness campaigns for parents | 2018 | June | M24 | ABAE
| P1.11 | ClimACT Resource-Matching Platform | 2017 | June | M12 | ISQ
WP2 | P2.1 | ClimAct Decision Support Tool final version | 2019 | April | M34 | Edigreen
| P2.2 | ClimACT benchmarking platform | 2017 | July | M13 | Edigreen
| P2.3 | Methodology for cost benefit analysis | 2017 | December | M18 | Ciemat
| P2.4 | Energy Performance Contracts business models | 2017 | June | M12 | ISQ
| P2.5 | ClimACT Educational Platform forActive Learning | 2017 | June | M12 | ABAE
| P2.6 | Strategies to include the ClimACT LCE contents and activities in the curricula | 2017 | July | M13 | ABAE
WP3 | P3.1 | Implementation of the LCE methodology in 35 schools | 2019 | March | M33 | USE
| P3.2 | Methodology to implement a LCE in schools | 2019 | April | M34 | USE
| P3.3 | ClimACT tools validated | 2019 | April | M34 | Edigreen
| P3.4 | Strategic action plans conducting to a LCE in SUDOE schools | 2019 | April | M34 | USE

## Deliverables
Deliverables
| Ref | Name | Deadline |  |  | Responsible
WP1 | E1.1.1 | ClimACT Gateway | 2016 | 31 October | M4 | IST
| E1.2.1 | Reports of meetings with stakeholders and foccus group discussions | 2019 | 31 May | M35 | UniGib
| E1.3.1 | Inventory of the results of other projects and platforms | 2016 | September | M3 | UniGib
| E1.3.2 | Report of the networking activities | 2019 | 31 May | M35 | UniGib
| E1.4.1 | ClimACT Academy digital dossier | 2019 | 30 April | M34 | IST
| E1.5.1 | ClimACT Resource-Matching Platform | 2017 | 15 June | M12 | ISQ
WP2 | E2.1.1 | Document with the structure of the OP of the ClimACT Decision Support Tool | 2016 | 30 September | M3 | Edigreen
| E2.1.2 | ClimACT Decision Support Tool V1 | 2017 | 31 May | M11 | Edigreen
| E2.1.3 | Manual of the ClimACT Decision Support Tool V1 | 2017 | 31 May | M11 | Edigreen
| E2.2.1 | Database module | 2016 | 31 December | M6 | Edigreen
| E2.2.2 | Database for 1000 schools | 2019 | 30 April | M34 | IST
| E2.3.1 | Key performance indicators | 2016 | 30 November | M5 | Edigreen
| E2.3.2 | KPI Generator Module | 2017 | 28 February | M8 | Edigreen
| E2.4.1 | Building Scenario Module | 2017 | 31 March | M9 | Edigreen
| E2.5.1 | LCA Module | 2017 | 31 March | M9 | Ciemat
| E2.6.1 | Cost Benefit Assessment Module | 2017 | 30 April | M10 | Ciemat
| E2.7.1 | Easy Guide on EPC Business Models | 2017 | 30 June | M12 | ISQ
| E2.7.2 | Recomendations for governments EPC | 2017 | 30 June | M12 | ISQ
| E2.8.1 | Guidelines for implementing learning activities | 2016 | 31 October | M4 | ABAE
| E2.9.1 | E-learning course on Sustainable Development | 2017 | 1 March | M9 | ABAE
| E2.10.1 | Teaching material for teachers | 2017 | 31 May | M11 | ABAE
| E2.10.2 | Teaching material for students | 2017 | 31 May | M11 | ABAE
| E2.11.1 | Electronic serious games | 2017 | 31 May | M11 | ABAE
| E2.11.2 | Missions of the physical games | 2017 | 31 May | M11 | ABAE
WP3 | E3.1.1 | Definition of the LCE committee,work plan and eco-codes in schools | 2016 | 31 December | M6 | ABAE
| E3.2.1 | Guidelines for energy and environment audits in schools | 2017 | 31 January | M7 | IST
| E3.2.2 | Report on baseline energy and environment performance | 2017 | 30 June | M12 | IST
| E3.3.1 | Short and long term targets | 2017 | 31 December | M18 | USE
| E3.3.2 | Best available actions and smart control strategies | 2017 | 31 December | M18 | USE
| E3.4.1 | Report on implementation of action plans | 2018 | 31 August | M26 | USE
| E3.5.1 | Report of the evaluation of the LCE strategies implementation | 2019 | 31 March | M33 | USE
WPT1 | ET2.1.1 | Logo | 2016 | 30 September | M3 | IST
| ET2.2.1 | Website | 2016 | 30 September | M3 | IST
| ET2.3.1 | ClimACT Final Event | 2019 | 31 May | M35 | IST
| ET2.4.1 | Poster with the information about the project (minimum size A3) | 2016 | 31 August | M2 | IST
WPT2 | ET3.1.1 | Monitoring protocol | 2016 | 31 August | M2 | IST
| ET3.2.1 | Financial audit | 2019 | 30 September | M39 | IST
| ET3.3.1 | Quality Assurance Plan | 2016 | 31 August | M2 | IST

## All Deadlines
WP
| Year | Month | Activity | WP1 | WP2 | WP3 | Managment | Communication | Monitorização | Status
M2 | 2016 | 31 August | Monitoring protocol | [5 empty] | ET3.1.1 | 50% | IST
M2 | 2016 | 31 August | Poster with the information about the project (minimum size A3) |  |  |  |  | ET2.4.1 |  | 0% | All
M2 | 2016 | 31 August | Quality Assurance Plan | [5 empty] | ET3.3.1 | 50% | IST
M3 | 2016 | 12 September | Inputs from partners to the ClimACT Gateway modules | A1.1 | [5 empty] | 0% | All
M3 | 2016 | September | Graphical Identity |  |  |  |  | T2.1 |  | 0% | IST
M3 | 2016 | 30 September | Logo |  |  |  |  | ET2.1.1 |  | 0% | IST
M3 | 2016 | 30 September | Website |  |  |  |  | ET2.2.1 |  | 0% | IST
M3 | 2016 | September | Branding elements |  |  |  |  | T2.1 |  | 0% | IST
M3 | 2016 | September | Facebook Page, Linkedin group,instagram and twiter |  |  |  |  | T2.5 |  | 0% | IST
M3 | 2016 | September | Dissemination and Communication Plan |  |  |  |  | T2.6 |  | 50% | IST
M3 | 2016 | September | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | IST
M3 | 2016 | September | Meetings with stakeholders in Lisbon, Seville, La Rochelle, Madrid and Gibraltar | A1.2 | [5 empty] | 0% | UniGib
M3 | 2016 | September | Database with relevant projects and platforms | A1.3 | [5 empty] | 0% | UniGib
M3 | 2016 | September | Inventory of the results of other projects and platforms | E1.3.1 | [5 empty] | 0% | UniGib
M3 | 2016 | 30 September | Document with the structure of the OP of the ClimACT Decision Support Tool |  | E2.1.1 |  |  |  |  | 0% | Edigreen
M4 | 2016 | 15 October | Preparation of questionnaires for Pre-audit |  |  | A3.2 |  |  |  |  | ISQ, IST, ULR
M4 | 2016 | 31 October | ClimACT Gateway | P1.1, E1.1.1 | [5 empty] | 0% | IST
M4 | 2016 | October | Network of stakeholders,end-users and other project teams | P1.2 | [5 empty] | 0% | UniGib
M4 | 2016 | October | Contact other projects and platforms | A1.3 | [5 empty] | 0% | UniGib
M4 | 2016 | October | ClimACT Open Forum and Networking online | A1.1 | [5 empty] | 0% | UniGib/IST
M4 | 2016 | 31 October | Guidelines for implementing learning activities |  | E2.8.1 |  |  |  |  | 0% | ABAE
M4 | 2016 | 31 October | Input for each course - ClimACT Academy | A1.4 | [5 empty] | 0% | ABAE/ISQ/Edigreen
M5 | 2016 | 30 November | Key performance indicators |  | E2.3.1 |  |  |  |  | 0% | Edigreen
M5 | 2016 | 30 November | Pre-audit |  |  | A3.2 |  |  |  | 0% | ISQ,IST,ULR,USE,UniGib
M6 | 2016 | December | Financial Report |  |  |  | T1.5 |  |  | 0% | All
M6 | 2016 | December | Newsletter |  |  |  |  | T2.5 |  | 0% | All
M6 | 2016 | December | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M6 | 2016 | October | Promotional Video |  |  |  |  | T2.5 |  | 0% | IST
M6 | 2016 | 31 December | Database module |  | E2.2.1 |  |  |  |  | 0% | Edigreen
M6 | 2016 | 31 December | Definition of the LCE committee,work plan and eco-codes in schools |  |  | E3.1.1 |  |  |  | 0% | ABAE
M6 | 2016 | 31 December | Audits’ guidelines with report format per sector |  |  | A3.2 |  |  |  | 0% | ISQ, IST, ULR
M7 | 2017 | January | Steering Committe meeting in Seville |  |  |  | T1.3 |  |  | 0% | USE
M7 | 2017 | January | Foccus Group discussion in Seville | A1.2 | [5 empty] | 0% | Ugib
M7 | 2017 | January | ClimACT Academy Infrastructue | P1.4 | [5 empty] | 0% | IST
M7 | 2017 | 31 January | ClimACT Academy online | A1.1 | [5 empty] | 0% | IST
M7 | 2017 | 31 January | Guidelines for energy and environment audits in schools |  |  | E3.2.1 |  |  |  | 0% | IST
M7 | 2017 | 31 January | Audits’ report format |  |  | A3.2 |  |  |  | 0% | IST
M8 | 2017 | 28 February | KPI Generator Module |  | E2.3.2 |  |  |  |  | 0% | Edigreen
M9 | 2017 | March | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M9 | 2017 | 31 March | Building Scenario Module |  | E2.4.1 |  |  |  |  | 0% | Edigreen/USE
M9 | 2017 | 31 March | LCA Module |  | E2.5.1 |  |  |  |  | 0% | ISQ
M9 | 2017 | 1 March | E-learning course on Sustainable Development |  | E2.9.1 |  |  |  |  | 0% | ABAE
M10 | 2017 | April | E-learning course on Sustainable Development | P1.7 | [5 empty] | 0% | ABAE
M10 | 2017 | 30 April | Cost Benefit Assessment Module |  | E2.6.1 |  |  |  |  | 0% | CIEMAT
M10 | 2017 | 30 April | On-site measurements and upload of results in database |  |  | A3.2 |  |  |  | 0% | ISQ,IST,ULR,USE,UniGib
M11 | 2017 | 1 May | Contents - Training Course ClimACT decision support tool operation | A1.4 | [5 empty] | 0% | Edigreen
M11 | 2017 | 1 May | Contents - Trainning Courses on ClimACT Educational Tools (related with E2.10.1, E2.10.2, E2.11.1,E2.11.2) | A1.4 | [5 empty] | 0% | ABAE
M11 | 2017 | 14 May | KPI generation |  |  | A3.2 |  |  |  | 0% | Edigreen
M11 | 2017 | 31 May | ClimACT Decision Support Tool V1 |  | E2.1.2 |  |  |  |  | 0% | Edigreen
M11 | 2017 | 31 May | Manual of the ClimACT Decision Support Tool V1 |  | E2.1.3 |  |  |  |  | 0% | Edigreen
M11 | 2017 | 31 May | Teaching material for teachers |  | E2.10.1 |  |  |  |  | 0% | ABAE
M11 | 2017 | 31 May | Teaching material for students |  | E2.10.2 |  |  |  |  | 0% | ABAE
M11 | 2017 | 31 May | Electronic serious games |  | E2.11.1 |  |  |  |  | 0% | ABAE
M11 | 2017 | 31 May | Missions of the physical games |  | E2.11.2 |  |  |  |  | 0% | ABAE
M11 | 2017 | 31 May | Schools Audit report |  |  | A3.2 |  |  |  | 0% | ISQ,IST,ULR,USE,UniGib
M12 | 2017 | June | Progress Report |  |  |  | T1.4 |  |  | 0% | IST
M12 | 2017 | June | Financial Report |  |  |  | T1.5 |  |  | 0% | All
M12 | 2017 | June | Financial Report |  |  |  | T1.5 |  |  | 0% | IST
M12 | 2017 | June | Financial audit | [5 empty] | T3.2 | 0% | External auditor
M12 | 2017 | June | Newsletter |  |  |  |  | T2.5 |  | 0% | All
M12 | 2017 | June | Dissemination and Communication Plan Update |  |  |  |  | T2.6 |  | 0% | IST
M12 | 2017 | June | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M12 | 2017 | June | Training course on the ClimACT decision support tool operation | P1.5 | [5 empty] | 0% | Edigreen
M12 | 2017 | June | Training course on the ClimACT educational tools operation | P1.8 | [5 empty] | 0% | ABAE
M12 | 2017 | 15 June | ClimACT Resource-Matching Platform | P1.11, E1.5.1 | [5 empty] | 0% | ISQ
M12 | 2017 | 30 June | ClimACT Resource-Matching Platform online | A1.1 | [5 empty] | 0% | ISQ/IST
M12 | 2017 | June | Energy Performance Contracts business models |  | P2.4 |  |  |  |  | 0% | ISQ
M12 | 2017 | June | ClimACT Educational Platform forActive Learning |  | P2.5 |  |  |  |  | 0% | ABAE
M12 | 2017 | 30 June | Easy Guide on EPC Business Models |  | E2.7.1 |  |  |  |  | 0% | ISQ
M12 | 2017 | 30 June | Recomendations for governments EPC |  | E2.7.2 |  |  |  |  | 0% | ISQ
M12 | 2017 | 30 June | Report on baseline energy and environment performance |  |  | E3.2.2 |  |  |  | 0% | IST
M13 | 2017 | July | Steering Committe meeting in La Rochelle |  |  |  | T1.3 |  |  | 0% | ULR
M13 | 2017 | July | Foccus Group discussion in La Rochelle | A1.2 | [5 empty] | 0% | Ugib
M13 | 2017 | July | ClimACT benchmarking platform |  | P2.2 |  |  |  |  | 0% | Edigreen
M13 | 2017 | 31 July | ClimACT benchmarking platform online | A1.1 | [5 empty] | 0% | Edigreen/IST
M13 | 2017 | July | Strategies to include the ClimACT LCE contents and activities in the curricula |  | P2.6 |  |  |  |  | 0% | ABAE
M14 | 2017 | 01 August | Contents - Seminars on business models | A1.4 | [5 empty] | 0% | ISQ
M15 | 2017 | 01 September | Contents - Awareness-raising campaigns with presentation of ClimACT gamification approaches | A1.4 | [5 empty] | 0% | ABAE
M15 | 2017 | September | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M15 | 2017 | September | Seminar on businessmodels for ESCO | P1.6 | [5 empty] | 0% | ISQ
M16 | 2017 | October | Awareness campaigns with presentation of ClimACT gamification approaches | P1.9 | [5 empty] | 0% | ABAE
M17 | 2017 | November | [7 empty] | 0%
M18 | 2017 | December | Financial Report |  |  |  | T1.5 |  |  | 0% | All
M18 | 2017 | December | Newsletter |  |  |  |  | T2.5 |  | 0% | All
M18 | 2017 | December | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M18 | 2017 | December | Methodology for cost benefit analysis |  | P2.3 |  |  |  |  | 0% | Ciemat
M18 | 2017 | 31 December | Short and long term targets |  |  | E3.3.1 |  |  |  | 0% | USE
M18 | 2017 | 31 December | Best available actions and smart control strategies |  |  | E3.3.2 |  |  |  | 0% | USE
M19 | 2018 | January | Meetings with stakeholders in Lisbon, Seville, La Rochelle, Madrid and Gibraltar | A1.2 | [5 empty] | 0% | Ugib
M19 | 2018 | January | External Advisory Board Meeting in Madrid |  |  |  | T1.2 |  |  | 0% | CIEMAT
M19 | 2018 | January | Steering Committe meeting in Madrid |  |  |  | T1.3 |  |  | 0% | CIEMAT
M19 | 2018 | January | Foccus Group discussion in Madrid | A1.2 | [5 empty] | 0% | Ugib
M20 | 2018 | February | [7 empty] | 0%
M21 | 2018 | March | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M22 | 2018 | April | [7 empty] | 0%
M23 | 2018 | 01 May | Contents - Awareness-raising campaigns prepared by children | A1.4 | [5 empty] | 0% | ABAE
M24 | 2018 | June | Progress Report |  |  |  | T1.4 |  |  | 0% | IST
M24 | 2018 | June | Financial Report |  |  |  | T1.5 |  |  | 0% | All
M24 | 2018 | June | Financial Report |  |  |  | T1.5 |  |  | 0% | IST
M24 | 2018 | June | Financial audit | [5 empty] | T3.2 | 0% | External auditor
M24 | 2018 | June | Newsletter |  |  |  |  | T2.5 |  | 0% | All
M24 | 2018 | June | Dissemination and Communication Plan Update |  |  |  |  | T2.6 |  | 0% | IST
M24 | 2018 | June | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M24 | 2018 | June | Awareness campaigns for parents | P1.10 | [5 empty] | 0% | ABAE
M25 | 2018 | July | [7 empty] | 0%
M26 | 2018 | August | Steering Committe meeting Gibraltar |  |  |  | T1.3 |  |  | 0% | Ugib
M26 | 2018 | August | Foccus Group discussion in Gibraltar | A1.2 | [5 empty] | 0% | Ugib
M26 | 2018 | 31 August | Report on implementation of action plans |  |  | E3.4.1 |  |  |  | 0% | USE
M27 | 2018 | September | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M28 | 2018 | October | [7 empty] | 0%
M29 | 2018 | November | [7 empty] | 0%
M30 | 2018 | December | Financial Report |  |  |  | T1.5 |  |  | 0% | All
M30 | 2018 | December | Newsletter |  |  |  |  | T2.5 |  | 0% | All
M30 | 2018 | December | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M31 | 2019 | January | [7 empty] | 0%
M32 | 2019 | February | [7 empty] | 0%
M33 | 2019 | March | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M33 | 2019 | 31 March | Report of the evaluation of the LCE strategies implementation |  |  | E3.5.1 |  |  |  | 0% | USE
M33 | 2019 | March | Implementation of the LCE methodology in 35 schools |  |  | P3.1 |  |  |  | 0% | USE
M33 | 2019 | April | Methodology to implement a LCE in schools |  |  | P3.2 |  |  |  | 0% | USE
M34 | 2019 | 30 April | ClimACT Academy digital dossier | E1.4.1 | [5 empty] | 0% | IST
M34 | 2019 | April | ClimAct Decision Support Tool final version |  | P2.1 |  |  |  |  | 0% | Edigreen
M34 | 2019 | 30 April | Database for 1000 schools |  | E2.2.2 |  |  |  |  | 0% | IST
M34 | 2019 | April | ClimACT tools validated |  |  | P3.3 |  |  |  | 0% | USE
M34 | 2019 | April | Strategic action plans conducting to a LCE in SUDOE schools |  |  | P3.4 |  |  |  | 0% | USE
M35 | 2019 | May | Meeting with the External Advisory Board in Lisbon |  |  |  | T1.2 |  |  | 0% | IST
M35 | 2019 | May | Steering Committee meeting in Lisbon |  |  |  | T1.3 |  |  | 0% | IST
M35 | 2019 | May | Foccus Group discussion in Lisbon | A1.2 | [5 empty] | 0% | Ugib
M35 | 2019 | 31 May | ClimACT Final Event |  |  |  |  | ET2.3.1 |  | 0% | IST
M35 | 2019 | May | Newsletter |  |  |  |  | T2.5 |  | 0% | All
M35 | 2019 | May | Promotional Video |  |  |  |  | T2.5 |  | 0% | IST
M35 | 2019 | May | Meetings with stakeholders in Lisbon, Seville, La Rochelle, Madrid and Gibraltar | A1.2 | [5 empty] | 0% | Ugib
M35 | 2019 | 31 May | Reports of meetings with stakeholders and foccus group discussions | E1.2.1 | [5 empty] | 0% | Ugib
M35 | 2019 | 31 May | Report of the networking activities | E1.3.2 | [5 empty] | 0% | Ugib
M36 | 2019 | 30 June | Dissemination and Communication Plan Update |  |  |  |  | ET2.6.1 |  | 0% | IST
M36 | 2019 | June | Monitoring report from WP leaders, communication and financial managers and PC | [5 empty] | T3.2 | 0% | All
M36 | 2019 | 30 June | Dissemination results digital dossier |  |  |  |  | ET2.5.1 |  | 0% | IST
M37 | 2019 | June | Layman Report |  |  |  |  | T2.5 |  | 0% | IST
M39 | 2019 | September | Final Report |  |  |  | T1.4 |  |  | 0% | IST
M39 | 2019 | September | Financial Report |  |  |  | T1.5 |  |  | 0% | All
M39 | 2019 | September | Financial Report |  |  |  | T1.5 |  |  | 0% | IST
M39 | 2019 | 30 September | Financial audit | [5 empty] | ET3.2.1 | 0% | External auditor
M39 | 2019 | September | After-ClimACT plan |  |  |  | T1.7 |  |  | 0% | IST

## Indicators
| Products |  | Indicators | Objective | Status
| Ref | Name
WP1 | P1.1 | ClimACT Gateway | No of visits | 10000
|  |  | No. of sign-up | 1000
| P1.2 | Network of stakeholders,end-users and other project teams | No. of events | 14
|  |  | No. of participants | 500
| P1.4 | ClimACT Academy Infrastructue | No. of activities | 114
| P1.5 | Training course on the ClimACT decision support tool operation | No. of editions | 6
|  |  | No. of trainees | 300
| P1.6 | Seminar on business models for ESCO | No. of editions | 2
|  |  | No. of trainees | 35
| P1.7 | E-learning course on Sustainable Development | No. of trainees | 300
| P1.8 | Training course on the ClimACT educational tools operation | No. of editions | 35
|  |  | No. of trainees | 420
| P1.9 | Awareness campaigns with presentation of ClimACT gamification approaches | No. of editions | 140
|  |  | No. of trainees | 6000
| P1.10 | Awareness campaigns for parents | No. of editions | 35
|  |  | No. of trainees | 1400
| P1.11 | ClimACT Resource-Matching Platform | No. of users during the project | 15
WP2 | P2.1 | ClimAct Decision Support Tool final version | No. of sucessful instalations | 35
| P2.2 | ClimACT benchmarking platform | No. of visulizations | 1000
| P2.3 | Methodology for cost benefit analysis | No. of downloads | 100
| P2.4 | Energy Performance Contracts business models | No. of downloads | 100
| P2.5 | ClimACT Educational Platform forActive Learning | No. of contents/activities developed | 30
| P2.6 | Strategies to include the ClimACT LCE contents and activities in the curricula | No. of downloads | 500
WP3 | P3.1 | Implementation of the LCE methodology in 35 schools | No. of pilot schools | 35
|  |  | No. of regions | 6
|  |  | No. of municipalities | 10
|  |  | No. of students | 12000
|  |  | No. of teachers | 300
|  |  | No. of school managers | 35
|  |  | No. of families | 12000
| P3.2 | Methodology to implement a LCE in schools | No. of downloads | 300
| P3.3 | ClimACT tools validated | No. of schools where the ClimACT Tools were validated | 35
|  |  | No. of students trained by ClimACT learning methodologies | 12000
|  |  | No. of business models tested in the pilot schools | 4
| P3.4 | Strategic action plans conducting to a LCE in SUDOE schools | No. of measures identified | 50